## Roadmap
Phase | Objectives | Deliverables | Dependencies | Risks | Success Criteria
1 Foundation | Project setup, theme, i18n, API client, query client, routing baseline | App shell skeleton, design tokens, Axios client, query provider, base routes | Governance approval; backend base URL | Teams diverge before standards are enforced | One running shell; lint/type/test pipeline; tokens applied
2 Authentication and shell | JWT/IdP integration and dynamic navigation | Auth provider, route guards, menu guards, permission catalog client | IdP metadata; JWT claims | Refresh/logout unavailable from backend evidence | Authenticated user can load guarded dashboard and menu
3 Core business modules | Implement reusable workbench pattern for modules | Workbench pages, tables, detail drawers, command action panels | Workbench APIs and DTO catalog | Generic workbench data lacks display metadata | Top 8 operational modules available with list/detail/search
4 Topology and visualization | Operational GIS map | Leaflet map, layers, GeoJSON rendering, search, popups, legend | Topology map APIs | Pipeline systems/pipelines not explicit layers | Operators visualize facilities, nodes, segments and connections
5 Workflow optimization | Workflow queues and validation interactions | Workflow workbench, validation action panels, notifications | Workflow state/action metadata | Exact states unavailable | Validators can process backend-supported actions safely
6 Operational excellence enhancements | Realtime, dashboards, analytics and executive reporting | Realtime event feed, dashboards, saved views, export, audit UX | SSE/STOMP stability; analytics/reporting APIs | Provider integrations and event semantics incomplete | Control-room and manager scenarios pass UAT

## Risks
Backend Capability | Frontend Impact | Risk | Recommendation
24 business modules under dz.sh.hidra.modules | Use modular route ownership and feature folders per module. | Teams may duplicate cross-module UI patterns. | Adopt one module shell template and central workbench components.
Spring MVC controllers and capabilities endpoints | Can discover operations and expose module actions. | Command routes may lack rich list/detail semantics for some use cases. | Use generic workbench APIs for list/detail/search and command aliases for actions.
Generic operational workbench APIs | Enables resource lists/detail/search for all JPA-backed resources. | Generic records may not provide business-friendly display fields. | Create frontend column metadata adapters and request backend display metadata later if needed.
Derived permission catalog APIs | Can drive menu/route/action guards from backend route metadata. | Catalog is metadata-only; no route-specific @PreAuthorize evidence. | Treat permissions as display/guard contract, not as proof of backend enforcement.
Topology GIS GeoJSON endpoints | Leaflet map can render layers, search and popups. | Pipeline systems and pipelines are not explicit layers unless backend adds them. | Visualize pipeline segments now; request explicit pipeline-systems and pipelines layers for enterprise GIS grouping.
JWT resource-server security | Use bearer tokens and role/scope claims. | No local login or refresh endpoint. | Integrate with enterprise IdP; do not invent HidraAPI login API.
ProblemDetail global error handling | Standard error contract can support toast/dialog/form mapping. | Field-level error shape may vary. | Central Axios error normalizer around ProblemDetail fields.
Async notification push and realtime SSE/STOMP | Can show live notification/event surfaces. | Provider push gateway is local placeholder. | Separate UI notification center from provider delivery semantics.